Draft for Final Project

List of potential [improvements?] to hiring practices to increase retention

- Hiring more minors could possibly help turnover

  - Followup: Do minors tend to stay longer than a year?

- Possibly implementing a referral program

  - Followup: Research into other companies that have implemented a referral program. Could also look at social experiments that have been conducted.

- Incorporate a CSR in the job description

- Stuff about potential for advancement

- Implenting the open door policy in a way that works better for people so they feel like they can speak up. – communication stuff

- Sundown policy – maybe preventing that in some way to

Patrick Timeline

Week 5 of internship

- Monday: Finalize Survey, finish informal outline of project, and secure ipad for survey tomorrow at 2pm.

- Tuesday: Let Jenn know the informal outline of the project so that we can adjust it to specifications. Also discuss with all ASMs beforehand.

- Wednesday: Market manager will be visiting.

- Thursday: Present formal plan to Jenn for feedback

- Friday: Present reviewed plan to Jenn/Patrick with feedback implemented

Week 6

- Working with Academy and Overnight teams, begin to implement project

- Monday: Potential start date for project

Week 7

- Continue Project, collect and implement feedback halfway through. Pivot to collecting metrics from ASMs. Making sure that program is actually being carried out.

Week 8

- Finish project on Friday

Week 9

- Project review and writeup.

Basic Description of Planned Project:

Purpose: To reduce store turnover from 130% to 100% in the long run

How we will we reduce turnover: We will have 1 supervisor meet for 15 minutes each week with all new hires to discuss the open door policy, the sundown policy, the expectations that new hires can have of management, and discuss job satisfaction of the employee.

Suggested questions for associate:

- How are you adjusting to the sleep schedule?

- How are you adjusting to your new job?

- Are you aware of the open door policy? If not, supervisor explains.

- Are you familiar with the sundown rule?

- Are you familiar with all of your job expectations?

- Do you have all of the tools to do your job?

- What are your hobbies outside of work?

Supervisor can go over path of promotion (in pathways, etc).

Supervisor can add own experiences at Walmart, and encourage the associate to stay with Walmart in order to be promoted or because it’s an encouraging work environment.

Give associate some time on the wire to check pathways, get familiar with one best way, etc. This could be 15 minutes as well.

This project sould be carried out on one-truck nights halfway to the end of the shift. This should not replace their break, but supplement their understanding.

The purpose of this is to talk and make them feel comfortable with you. We believe that coaching by walking around is effective, but too brief to develop a personal relationship with a supervisor.

How we will measure this: During the ‘people’ discussion Jenn and Tonya measure turnover. This meeting will happen on 6/26, and then again in 4 weeks. We will be able to determine if turnover has decreased due to our program.

If its 130% its about 10 months on average.

You get paid for orientation, you are less efficient, you have to be trained for your specific job. Hiring costs about 6000/year just on indeed. 1500-2000.

What times work best

Overnight – After truck is unloaded. Maybe in the last 3 hours of their shift. Because that’s usually when you have some time.

CAP 1 4am-1pm

CAP 2 2pm-11pm

Cashiers – all hours.

CSM will be responsible for cashiers

But CSM and Cashiers could do it at the same time, theoretically.

ASMs will be responsible for completing the hour each week with associates

Gary – Frontlines

Kim – Middle

Sheri – Garden/Sports/Toys

Bert – Back

Zack – fresh

Grocery- Daniel

Produce/Food

15 minutes

New a